## Sheet1
PBIs | PBI: 01 | PBI: 02 | PBI: 03 | PBI: 04 | PBI: 05 | PBI: 06 | PBI: 07 | PBI: 08 | PBI: 09
As <user role/persona> I want <what?> So that <why?> Note: | As an Election Official I want CPL ties to work so that CPL elections fully work | As an Election Official I want the Audit File produced after an election to be in the correct format for CPL So that I can understand the election information easier at a glance | As the election official I want to be able to input multiple files for all elections. So that I am able to run files from multiple voting locations. | As the election official I want the voting system to be able to handle multiple IRV files for the election. So that I am able to run a election with votes from multiple voting locations. | As the election official I want the Voting System to be able to handle multiple CPL files that I give it. So that I am able to run a election with votes from multiple voting locations. | As an Election Official I want to see a table at the end of an IRV election So that I can see the stats of each candidate at each round | As the election official I want the Voting System to be able to handle multiple PO files that I give it. So that I am able to run a election with votes from multiple voting locations. | As a product owner I want the voting system to process PO ballots. So that the election is able to run the Popularity Only algorithm. | As a Election Official I want the voting systen to be able to run PO elections and detremine a winner. (No audit file or anything, just needs to work)
Acceptance Criteria (conditions that have to be fulfilled to ensure the story is complete) | CPL ballot files that would result in a tie give a clear winner based on 50/50 coin toss. | Audit file looks clean and organized All winners should listed by their parties Number of candidates should be correct | Multiple file names are able to be inputted into the program Only valid files are processed | Completely gather all the information from all IRV election files. | Completely gather all the information from all CPL election files. | I should be able to see all of the rounds showing the number of votes each candidate received at each round along with the votes that were added at that round or substracted if the candidate was dropped | Completely gather all the information from all PO election files. | - The PO ballots have been recieved and are now ready for processing. | - A winner is choosen by the end off sunning the election
Definition of Done (what is required by the team before sending out for review) | Function that correctly parses through party votes checking for ties between two or more parties. Then call a function that randomly selects one of these parties to be the winner | All information from the election has been correctly collected Testing has been done for audit file production Formatting is consistent between all examples All candidates/parties/winners should be listed properly (comma seperated) | Method of inputting multiple files has been developed All file names have been saved in a list for future use Testing has been done for receiving multiple files | - Have all information in header parsed and saved - Combine all of the information gathered from every file into 1 file. - Have the correct amout of ballots calculated | - Have all information in header parsed and saved - Combine all of the information gathered from every file into 1 file. - Have the correct amout of ballots calculated | The table is displayed correctly The information displayed is correct | - Have all information in header parsed and saved - Combine all of the information gathered from every file into 1 file. - Have the correct amout of ballots calculated | - Save the PO ballots into a data structure - Distruibute PO ballots to each candiate | - After the ballots are distruibuted they are compared to see who is the winner of the election - Even if there is a tie a winner is decided
Effort: Small, Medium, Large, Extra Large (estimate of effort and time) OR number of hours needed | Medium: 3 hours | Small: 1 hour | small: 1.5 hour | small: 1.5 hour | small: 1.5 hour | Medium: requires the collection of information (from audit file) 2 - 3 hrs does not requires GUI or table creation can just be displayed in terminal | small: 1.5 hour | Medium: 2 hrs | Medium: 2 hrs
PBI Author(s) | Ethan Johnson | Camden Fessler | Camden Fessler | Maria Zavala | Maria Zavala | Aaron Raines | Maria Zavala | Maria Zavala | Maria Zavala
Not Started | Complete | Complete | Complete | Complete | Complete | In Progress | Complete | Complete | Complete
In Progress
Complete
Tasks | Tasks PBI: 01 | Tasks PBI: 02 | Tasks PBI: 03 | Tasks PBI: 04 | Tasks PBI: 05 | Tasks PBI: 06 | Tasks PBI: 07 | Tasks PBI: 08 | Tasks PBI: 09
| Determine correctly where ties occur | Changing the format for how info is read in (Audit File) | Prompt the user to input the file names in command line. Run loop that asks for multiple file names until user types 'done' | Parse the file and add save the number candidates into the "Complete Election File" - That will be the file used to run the election. | Parse the file and add save the number candidates into the "Complete Election File" - That will be the file used to run the election. | pull out the correct pieces of information: number of votes at each round added or substracted votes at each round | Parse the file and add save the number candidates into the "Complete Election File". | PO ballots are parsed and votes are counted | distribute the ballots to each candidate
| Call function to determine 50/50 tie | Changing how info is printed out in the audit file (Election) | Check if file name exists | Parse the file and add up the number of ballots for each file. | Parse the file and add up the number of ballots for each file. | identify where the different pieces of information are located | Parse the file and add up the number of ballots for each file. | Determine which candidate/party has the most votes | Compare the ballots each candidiate recieved
| Test ties work correctly |  | Discard file name if file does not exist | Parse the file and save all the names of candidates into the "Complete Election File" - That will be the file used to run the election. | Parse the file and save the number of parties into the "Complete Election File" - That will be the file used to run the election. | identify counts | Parse the file and save the number of parties into the "Complete Election File" - That will be the file used to run the election. |  | Once candidates get compared make sure to determine a winner
|  |  |  | Parse the file and save all the ballots from each file inputed into the "Complete Election File" - That will be the file used to run the election. | Parse the file and save the number of seats into the "Complete Election File" | figure out data structure to store this and spit it out | Parse the file and save the number of seats into the "Complete Election File" |  | Once candidates get compared make sure to determine a winner if there is a tie make sure to do a fair coin toss.
|  |  |  | Implement these functions into a while loop to handle multiple files | Parse the files and save candidates into the "Complete Election File" | call method to display the information collected for each round. | Parse the files and save candidates into the "Complete Election File" |  | Save the winner to a variable.
|  |  |  | Test that multiple IRV files can be processed for a single election | Implement these functions into a while loop to handle multiple files | test that it is running properly | Implement these functions into a while loop to handle multiple files |  | Print winner to audit file and to screen
[5 empty] | Test that multiple CPL files can be processed for a single election |  | Test that the PO system as a whole works with multiple files |  | Test that all functions in PO file are working individually