## Sheet1
PBIs
As <user role/persona> I want <what?> So that <why?> Note: | As a Election Official I want to save the PO results of all candidates in Audit file. So that we are able to keep track of who won and who lost. | As a Election Official I want to see the PO results of all candidates in Audit file. So that we are able to see who won and who lost. | As an Election Official I want a GUI set up for officials to use when inputting files into the system So that officials can easily pass election files into the program without using the terminal | As an Election Official I want the ballots for IRV to be validated. So that the election is more accurate. Note: | As an Election Official I want only valid IRV ballots to be used in election. So that the election is more accurate. Note:
Acceptance Criteria (conditions that have to be fulfilled to ensure the story is complete) | - Should have the stats of each candiate saved onto the audit file. | - Constituents who voted are able to know how well their candidate did in the election. | A GUI is availabile for all election officials to use when inputting files The GUI should not use the terminal It should be clean and organized, as well as easy to use | - All ballots will be checked. - All ballots will have at least half of the candidates ranked. - All ballots not properly filled out are discarded - There is a seperate file where all discarded ballots are stored | - All ballots are checked. - All valid ballots will be used for runing election.
Definition of Done (what is required by the team before sending out for review) | - Save the percentage of votes each candidate received | -Display the percentage of votes each candidate received | A GUI has been created using an external tool with point and click capabilities The GUI has been tested and does not crash without an error The GUI parses files into the election program | - All ballots are check for correctness - All ballots that are valid have at least half of the candidates ranked. - All ballots that are valid are now ready for processing. - IRV ballots that don't have at least half of the candidates ranked, rounded up from .5 or above to the next higher integer value, are invalidated | - All ballots are check for correctness - All ballots that are valid have at least half of the candidates ranked. - The file only contains valid ballots. - The invalid ballots are dropped from valid ballots file. - Only valid ballots are stored in the ballots counted in the IRV election Testing has been done for invalidating/storing ballots
Effort: Small, Medium, Large, Extra Large (estimate of effort and time) OR number of hours needed | Small: 1 hr | Small: 1 hr | Large: 3 days | Medium: 2 hrs | Small: 1 hr
PBI Author(s) | Maria Zavala | Maria Zavala | Camden Fessler | Maria Zavala | Maria Zavala
Status (Not Started, In Progress, Complete) | Not Started | Not Started | Not Started | Not Started | Not Started
Not Started
In Progress
Complete
Current Sprint
Tasks